## Sheet1
Item # | Plugin | Type | Description | Rev Log | Required for Alpha Release? | Status
1 | CCP | Feature | utilize DAQ mode instead of SHORT_UP for data streaming (faster) | 4/28/2026 - DAQ mode with 1ms, 10ms, 50ms, and 100ms tiers functional |  | OBSOLETE
2 | NI DAQ | Bug | Analog out doesn't seem to work, verify | 4/30/26 - works via UI inputs |  | COMPLETE
3 | Statistics | Feature | Full plugin workup | 4/30/26 - done |  | COMPLETE
4 | Calculated Channels | Upgrade | Streamline user workflow to generate/store calculations, possible large text window that allows for true python scripting? | 4/29/2026 - new UI with chainable expressions in single calc 'recipe'. |  | COMPLETE
5 | CCP | Feature | access secure server for ccp access keys instead of manual entry/env | 4/28/26 - manual entry updated for session persistance. Remembers keys until app restart, hides key entry with '*' 5/4/2026 - plan to link in with (hopefully) prebuilt server for ecm unlock (talk to aaron) 5/13/2026 - Aaron to build backend which matrix will send REST request for auth token with ecu type (econtrols vs mt88 vs weichai), seed from ecm, rev, and type (cal, prog and daq), expect by end of week 5/22 | Yes
6 | Loadbank | Feature | verify 1.5MW/700kW/Avtron functionality | 750kW complete 5/14/2026 - Reviewed 1.5MW setup, should work as 750KW works and setup is very similar but still need to test. 700kW mapping yaml updated and UI updated for heartbeat monitoring. Need to test | Yes | IN PROCESS
7 | Console | Upgrade | Red plugin rules | 4/29/2026 - CCP error states set | No | IN PROCESS
8 | Console | Upgrade | add logging of important events, errors to console terminal | 4/29/2026 - CCP plugin status and messaging (unlock status, access key errors, 'Unlock OK', polling info) | No | IN PROCESS
9 | Channel Manager | Bug | color coding alarms appears to only work on one alarm, even if more are configured | 4/30/2026 - set 2 warning and 1 alarm, all 3 color changes occurred across both displays | Yes | COMPLETE
10 | Omega | Feature | Verify functionality with hardware |  | No
11 | Server | Feature | Setup database for scales, test types, engine types, calculations that can be accessed via web (use Aaron template) - link to EngineTest |  | No
12 | Console | Upgrade | Graceful closeout, end xnet sessions, close NI daq tasks etc on exit | 5/4/2026 - exit closes out session for all plugins | Yes | COMPLETE
13 | All | Upgrade | Be able to exit plugin with empty setup |  | No
14 | All | Upgrade | UI should be standardized for 1080p screens | 5/5/2026 - Console sizing adjusted | No | IN PROCESS
15 | All | Feature | Confirm long recording quality (data point count, file splitting when past time limit etc) | 5/5/2026 - File split test with 5min segments PASS 5/5/2026 - Test files at 10hz show a diff of 3 rows in 1000, which is an acceptable amount of jitter 5/7/2026 - 1hr, 5loop cycle run. Exporting drove disconnects with telemetry, update done and tested, need to redo test. | Yes | IN PROCESS
16 | Launcher | Feature | Single launcher program, starts core, waits till complete then launches UI | 5/4/2026 - single command line launch complete, release will be compiled exe 5/14/2026 - exe with onedir setup (expect large). Store in network drives for distribution, build locally, use git for source code, include readme with necessary installs outside of onedir included files. | Yes | IN PROCESS
17 | CCP | Upgrade | change default polling to 100ms, users can increase polling to 50ms, 10ms, or 1ms if needed. |  |  | OBSOLETE
18 | CCP | Upgrade | Revert back to SHORT_UP as this matches Matrix, DAQ mode preserved in possible future hybrid model. This allows for more channels but possibly slower polling. | 4/29/2026 - HIGH/LOW polling setup with 75% HIGH 25% low default (configurable in yaml). LOW polling is default, users promote channels to HIGH when needed |  | COMPLETE
19 | UI | Upgrade | Add block for 'Analog Out' channels to 'All Channels Table' that is read/write | 4/29/2026 - Added, checked with louver control | Yes | COMPLETE
20 | UI | UI | Main Test Display 4 axis hides behind test info and watch channels table. Formatting/sizing issue, axis work fine just can't see them | 4/30/26 - margins fixed and added axis labelling. |  | COMPLETE
21 | Calculated Channels | Upgrade | Alias pickers are text input not channel selection | 5/5/2026 - complete | Yes | COMPLETE
22 | UI | Bug | Apparenlty the Main Test Display is somehow linked to the AI_Context.yaml file, need to fix that. | 4/30/2026 - fixed, added app_registry.yaml |  | COMPLETE
23 | CCP | Bug | Units don't appear to show up in channel list in config dialog | a2l parse was being done twice with two different functions (one for ccp read and one for config generation). Combined to single function and updated config such that channel selection + priority is retained on new a2l but address and channel info is updated. Missing channels listed if new a2l does not contain old channel list. | No | COMPLETE
24 | UI | Bug | Removing axis from plot channel list does not update the 'Y-axis Settings' table automatically. |  | No
25 | NI DAQ | Update | Configure NI DAQ channels table is not sized correctly, need to autosize based on | 4/30/2026 - fixed |  | COMPLETE
25 | CCP | Upgrade | CAN bus selection needs to be a dropdown not a text input |  | No
26 | All | Upgrade | Investigate alias picker as single UI as opposed to separate UI's that each plugin has built in? Simplify code |  | No
27 | All | Upgrade | Refactor to split up excessively long py scripts (CCP > 1600 lines as of 4/30/2026) | plan for orchestrator.py script refactor made, may push off till later. | No
28 | All | Bug | Config' should not be available while test is locked or recording | 5/6/2026 - complete | Yes | COMPLETE
29 | Statistics | Bug | Can't stop a log when it's already going, user should be able to interrupt a logging session (I fat fingered a 1000s log and couldn't stop it) |  | No
30 | Statistics | Feature | Need to test with live data the automatic trigger option |  | No
31 | CCP | Feature | Confirm primary/secondary data streams work in parallel | Confirmed | Yes | COMPLETE
32 | Channel Manager | Upgrade | Adjust column sizing in config window to see things better. |  | No | COMPLETE
33 | All | Bug | System channels need to be organized better, 'i' channels (alarms, estops, etc) |  | No
34 | UI | Update | Make NI channels that are not pressure go to 'Other' table |  | No | COMPLETE
35 | CCP | Update | SHORT_UP is very slow with a fully loaded list, seeing 0.2Hz with 40-50channels, this is not as good performance as Matrix I believe | SHORT_UP downtime fixed getting 1-1.5Hz with 45 channel, similar to matrix | Yes | COMPLETE
36 | All | Update | Make sure documentation is fully in line with current code for all plugins |  | No
37 | Core | Update | Add 'Test Time' to telemetry, starts at 0 when record button is hit. |  | No
38 | NI DAQ | Feature | Need to test alarm functionality, does it set an estop properly. | 5/7/2026 - louver alarm triggered estop circuit properly | Yes | COMPLETE
39 | All | Feature | Debug mode - telemetry/terminal printouts for timing and health of plugins |  | No
40 | All | Upgrade | Create splash icon for loading with loading bar |  | Yes | COMPLETE
41 | CCP | Bug | remove repeated error messages in terminal, error once and update if status change |  | No
42 | All | Feature | Determine how fresh installs work? What initial settings are assumed when a plugin is first used? | 5/6/2026 - docs\deployment_default_configs.md details what yamls are required for fresh install and which ones are generated on config | Yes | COMPLETE
43 | All | Feature | Detailed messaging on splash logo so user sees progress during large plugin load (CCP Starting… NI DAQ starting… Modbus Starting…. Etc |  | No
43 | NI DAQ | Update | Alias picker py called 'NIDAQAlias Picker' but is used across multiple plugins, rename for clarity |  | No
44 | Cycle | Update | Add visual to show current position in cycle. Match old matrix with graph, not just % bar | Added | No | COMPLETE
45 | Loadbank | Bug | Minimizing console also minimizes the load bank control screen | Fixed | Yes | COMPLETE
46 | Loadbank/Analog Out | Update | Refresh of user inputs needs to be snappier | 5/7/2026 - UI was refreshing config yamls at refresh rate, removed this and refresh went from ~300ms to 10ms | No | COMPLETE
47 | Analog Out | Update | closing the program should set all dig and analog outs to zero instead of retaining hteir last state | 5/7/2026 - update added, need to test | Yes
48 | Cycle | Update | make x/y discovery smarter, currently requires input to match the csv, should instead discover columns A and B and auto map to cycle. |  | No
49 | All Channels Table | Update | drop the 'emaster' 'eslave' prefix in display but not recording so the variables are more easily seen |  | No | COMPLETE
50 | Console | Bug | Exporting large excel files will at some point momentarily turn the console plugin tiles grey, need to understand why this happens and if it is truly breaking telemetry (safeties) | 5/7/2026 - 1hr (71983 rows) ~11min to export to excel 5/7/2026 - update applied to make export it's own py process that runs parallel to orchestrator. Test on laptop showed no disconnects and faster export (6min vs 11min) | Yes | COMPLETE
51 | Cycle | Bug | Final step not commanded, seems test ends just prior to final command instead of after. | 5/7/2026 - update added, need to test with short cycle | Yes
52 | CCP | Update | Investigate nan in TIPAdapt channels | Channels appear to come and go… ecm restarts, matrix running in between, some kind of channel warmup is occuring 5/14/2026 - TIPAdapt channels returned 0x32 notification code which SHORT_UP was ignoring, changed plugin to accept this and data streams now. | Yes | COMPLETE
53 | Displays | Update | Figure out better sizing for displays, crowded, lots of overlap. |  | No
54 | Calculated Channels | Bug | Need to investigate corrected power expression, getting nan, may be user error but I think all inputs are reading so output should also read | Was using incorrect power input name… | Yes | OBSOLETE
55 | UI | Update | NAN should be color coded for easy identification |  | No
56 | UI | Bug | CAN plugin channels are populating in Other table, not CAN table. | 5/14/2026 - appears to be an issue with how the table updates, it doesn't re-evaluate the channel list each time it updates after its been opened. | No | COMPLETE
57 | CCP | Bug | Unlock seems to still fallback to utilize env variables | 5/18/2026 - confirmed unlock is ok, ecm stays unlocked if not powered down (desktop setup) so once unlocked once, the 'key' in the config stops mattering until its powered down. | Yes
58 | Export | Update | Progress bar for export status |  | No
59 | Export | Feature | Standalone tool to pick sqlite file (or folder) and export instead of waiting for end of test or if crash occurs